## Variation register
TENDER READY TOOLS · FREE SUBCONTRACTOR VARIATION REGISTER
Variation register
One row per variation. Orange cells are inputs. Status drives the totals. Keep VAR numbers identical in notices, quotes and payment claims.
Project:
Subcontract no.:
Today:
VAR no. | Description | Directed by | Direction ref / date | Date aware | Notice due | Notice sent | Quote submitted | Response due | Claimed $ | Approved $ | Status | EOT days claimed | EOT days granted | In claim no. | Days to response | Flag | Notes
VAR-01 | Second LV feeder MSB-2 to pump station MCC (not on tender dwgs E-201 Rev B) | Site rep (written SI-014) | SI-014 03/11/2026 | [5 empty] | 18500 | 18500 | Approved |  |  | PC-04
VAR-02 | SCADA tag list Rev C re-termination, 46 cores | PM email | Email 10/11/2026 | [5 empty] | 38600 |  | Submitted | 3

## Summary
Variation summary by status
Status | Count | Claimed $ | Approved $
Draft
Notified
Submitted
Under review
Approved
Part-approved
Rejected
Disputed
Withdrawn
Total
Unapproved value at risk (Submitted + Under review + Disputed)
Overdue notices
Want notices, EOTs and BIF Act payment claims in one workbook? Subcontract Commercial Control Pack:
https://tenderready0.gumroad.com/l/alesb
General information only, not legal advice. Notice dates come from your contract; this register does not make a notice valid. Built by Tender Ready Tools, a Queensland-based engineer working in HV/LV project delivery.